## WBS-Template
Work Breakdown Structure Table
Project Title: | L06: Progress Report for Analysis Phase
Project Manager: | Shin Woo
Prepared by: | Christopher Paez
Project Sponsor: | QuickBooks
Date: | 2022-02-20
Level | WBS | Task Description | Completed? | Deadline
1 | 1 | Planning Phase | Yes | Jan. 23
2 | 1.1 | Group Contract | Yes | Jan.16
3 | 1.1.1 | Group Name | Yes | Jan.16
3 | 1.1.2 | Project Group Members and Sign-off | Yes | Jan.16
3 | 1.1.3 | Code of Conduct | Yes | Jan.16
3 | 1.1.4 | Participation | Yes | Jan.16
3 | 1.1.5 | Division of Work | Yes | Jan.16
3 | 1.1.6 | Communication | Yes | Jan.16
3 | 1.1.7 | Meeting Guidelines | Yes | Jan.16
2 | 1.2 | Project Definition Report | Yes | Jan. 23
3 | 1.2.1 | Purpose | Yes | Jan. 23
3 | 1.2.2 | Stakeholders | Yes | Jan. 23
3 | 1.2.3 | Scope | Yes | Jan. 23
3 | 1.2.4 | Operational Feasability | Yes | Jan. 23
3 | 1.2.5 | Benefits | Yes | Jan. 23
1 | 2 | Analysis Phase | Yes | Jan. 30
2 | 2.1 | Progress Report for Analysis Phase | Yes | Jan. 30
3 | 2.1.1 | Summary of the Project's Progress | Yes | Jan. 30
3 | 2.1.2 | Task Completed | Yes | Jan. 30
3 | 2.1.3 | Task Started | Yes | Jan. 30
3 | 2.1.4 | Task Expected | Yes | Jan. 30
3 | 2.1.5 | Problems | Yes | Jan. 30
3 | 2.1.6 | Updated WBS | Yes | Jan. 30
2 | 2.2 | Solutions Alternative Document | Yes | Feb. 6
3 | 2.2.1 | Contrast and Compare COTS | Yes | Feb. 6
3 | 2.2.2 | Develop a List of Non-COTS | Yes | Feb. 6
3 | 2.2.3 | Make a Non-COTS recommendation | Yes | Feb. 6
2 | 2.3 | Design Requirements Documents | Yes | Feb. 6
3 | 2.3.1 | Description of sub-problem solution | Yes | Feb. 6
3 | 2.3.2 | COTS package proposed | Yes | Feb. 6
3 | 2.3.3 | Finalized protocols | Yes | Feb. 6
3 | 2.3.4 | Complete description of design for all training, etc. | Yes | Feb. 20
2 | 2.4 | Progress Report for Analysis Phase | Yes | Feb. 20
3 | 2.4.1 | Summary of the Project's Progress | Yes | Feb. 20
3 | 2.4.2 | Task Completed | Yes | Feb. 20
3 | 2.4.3 | Task Started | Yes | Feb. 20
3 | 2.4.4 | Task Expected | Yes | Feb. 20
3 | 2.4.5 | Problems | Yes | Feb. 20
3 | 2.4.6 | updated WBS | Yes | Feb. 20
2 | 2.5 | Stakeholder Analysis | Yes | Feb. 20
3 | 2.5.1 | 3 Stakeholders Identified | Yes | Feb. 20
3 | 2.5.2 | Stakeholder's interest and reason for interest | Yes | Feb. 20
3 | 2.5.3 | Stakholder's power influence | Yes | Feb. 20
3 | 2.5.4 | Stakeholder's power influence justification | Yes | Feb. 20
1 | 3 | Design Phase | No | Mar. 20
2 | 3.1 | Rough Draft of Design Requirements | No | Mar. 6
3 | 3.1.1 | Descriptions of how each sub-problem is solved | No | Mar. 6
3 | 3.1.2 | Complete description of COTS package proposed | No | Mar. 6
3 | 3.1.3 | Finalized protocols developeid for any sub-problem | No | Mar. 6
3 | 3.1.4 | Complete description of the design for all training | No | Mar. 6
2 | 3.2 | Design Requirements Documents | No | Mar .20
3 | 3.2.1 | Description of how each sub-problem is solved by final ststem solution | No | Mar .20
3 | 3.2.2 | Complete description of COTS package proposed for tracking subproblem | No | Mar .20
3 | 3.2.3 | Finalized protocols | No | Mar .20
3 | 3.2.4 | Complete discription of design for all traning, webiste, etc. | No | Mar .20
1 | 4 | Implementation phase | No | Apr. 24
2 | 4.1 | Progress Report for Implementation Phase | No | Apr. 3
3 | 4.1.1 | Summary of the Project's Progress | No | Apr. 3
3 | 4.1.2 | Task Completed | No | Apr. 3
3 | 4.1.3 | Task Started | No | Apr. 3
3 | 4.1.4 | Task Expected | No | Apr. 3
3 | 4.1.5 | Problems | No | Apr. 3
3 | 4.1.6 | Updated WBS | No | Apr. 3
2 | 4.2 | Draft of Implementation Document | No | Apr. 17
3 | 4.2.1 | Solution to all subproblems addressed by the overall system | No | Apr. 17
3 | 4.2.2 | Complete documentation for the entire system solution | No | Apr. 17
3 | 4.2.3 | Previous submitted doucments with appropriate appendix for each | No | Apr. 17
3 | 4.2.4 | Executive summary of complete system for top management and be located at the beginning of the complete set of deliverables | No | Apr. 17
2 | 4.3 | Implementation Document | No | Apr. 24
| 4.3.1 | Solution to all subproblems addressed by the overall system | No | Apr. 24
| 4.3.2 | Complete documentation for the entire system solution | No | Apr. 24
| 4.3.3 | Previous submitted doucments with appropriate appendix for each | No | Apr. 24
| 4.3.4 | Executive summary of complete system for top management and be located at the beginning of the complete set of deliverables | No | Apr. 24

## Other_templates
Project Management Templates
Project Management Templates
The Top 50 Business Risks (and how to manage them)!
Issue Log Template [free download]
End Project Report Template
Risk Register Template
Stakeholder Management Templates
Work Breakdown Structure (WBS) Examples to download
WBS Dictionary